## Slide 1
The n3He Experiment
Michael Gericke
University of Manitoba
for the n3He collaboration
March 2014 FnPB Proposal Review & Advisory Committee Meeting

## Slide 2
Brief overview of the experiment
Schedule overview / summary (based on current status)
Current status of construction and recent progress
  Beamline components
  Magnetic holding field
  Spin rotator
  Target/detector chamber
  Preamplifers and DAQ
Installation and commissioning plans
Outline

## Slide 3
Spokespersons
D. Bowman, M. Gericke, C. Crawford
Local Project Manager
S. Penttila
Project Engineer
Jack Thomison
Work Subpackage Leaders
G. Greene Neutronics
L. Barrón Solenoid
C. Crawford Spin rotator
M. Gericke Target / detector
D. Bowman Preamplifiers
C. Crawford Data acquisition
N. Fomin Online analysis
J. Hamblen Integration
D. Bowman Commissioning
The n3He Collaboration

## Slide 4
10 Gauss
solenoid
RF spin rotator
3He target /
ion chamber
FnPB cold
neutron guide
3He Beam
Monitor
FNPB
n-3He
Measure PV spin asymmetry to 2x10-8
Longitudinal holding field – suppressing PC nuclear asymmetry:
(1.7x10-6  sn  kn x kp (Hale) suppressed by two small angles
RF spin flipper – negligible spin-dependence of neutron velocity
3He ion chamber – both target and detector
Experimental Setup

## Slide 5
Schedule Overview
Complete component construction / bench testing now - May
Preassemble in staging are May - June
Facility summer maintenance break June-27 – Aug-15
Removal of NPDGamma June-27 – July -7
Installation of n-3He on beam line July-7 - Aug-15
IRR August
Alignment of the experiment with beam Sep – Oct -2014
Commissioning; 60 days Oct – Nov - 2014
Measurement of PC transverse asymmetry; 15 days Dec - 2014
Facility winter maintenance break Dec - 2014 - Feb - 2015
Measurement of PV longitudinal asymmetry; 200 days Feb-2015 – Dec- 2015

## Slide 6
Experimental Setup

## Slide 7
Experimental Setup

## Slide 8
Unistructure support – preliminary CAD model
TOP VIEW

## Slide 9
Scope
  FnPB guide, polarizer, beam monitors – stays UNCHANGED
  PPS remains UNCHANGED
  Beam profile scanners, polarimetry
Status
  All equipment is being used for NPDG experiment except the beam profile scanners
  XY-scanners in hand and tested
Remaining work
  Design shielding and mounts for xy-scanner – April
  Design mount for 3He analyzer (polarimetry) – April
  Modify beamline shielding – April
Beamline
Chris Hayes, Kabir Latiful Josh Hamblen
Geoff Greene

## Slide 10
Magnetic Field

## Slide 11
Scope
  Magnetic field simulations to verify adiabatic spin rotation and uniformity
  Unistructure frame for Magnetic coils, Spin rotator, and Target/detector mounts directly onto existing NPDG stands on the beamline
  Design, construction, and testing of longitudinal solenoid 10 Gauss holding field, just like NDPG
Status
  Calculations indicate adiabaticity, coils being machined (winding in parallel) 18(+1) coils, 15 cm apart, 70(52) cm sides, 150 A turns
  Materials for frame and coil supports are in hand
Remaining work
  Machining of coil supports: April
  Coil completion: May
  Coil delivery to ORNL: June
Magnetic Field
Andrés Ramirez,
Libertad Barrón

## Slide 12
Spin Rotator

## Slide 13
Scope
  Design of RF double cos-theta coil
  Machining forms for inner/outer coils, aluminum enclosure, mounts
  RF driver electronics
  Field mapping and testing
Status
  Design complete
  Machining of coils complete
  Winding of coils Complete
  RF driver electronics exist and are being used for NPDG
Remaining work
  Construction of enclosure: In progress
  Testing and field mapping: In progress
Spin Rotator
Chris Hayes,
Geoff Greene
Chris Crawford

## Slide 14
Design and Construction:
Complete
Inner cylinder made from PVC
Outer coils fabricated using 3D print Technology.
Spin Rotator (Coils)

## Slide 15: Spin Rotator (Photographs)

## Slide 16
Target / Detector

## Slide 17
Scope
  Vacuum enclosure with 1 atm 3He
  144 channels of sense wires
  low leakage / noise
  good charge collection
Status
  Vacuum enclosure in hand
  Wires soldered to frames
Remaining work
  Assemble wire plane stack, readout plane: March
  HV test and vacuum tests March
  Fill with 3He: April
  Electronics noise testing with chamber April
Mark McCrea
Michael Gericke
Seppo Penttila
Target / Detector

## Slide 18
12” Conflat end flanges
1 mm Al windows
Fill gas: 1 atm 3He
Feedthroughs: 4x signal, 2x high voltage, 2x vacuum
Target / Detector (Housing)

## Slide 19
17 HV planes
16 signal planes
  144 signal wires
All wires soldered to frames
Mounting hardware and fittings all constructed
PCB readout boards will arrive late March
Assembly March-April
Testing starting in April
Target / Detector (Wire frame stack)

## Slide 20
Target / Detector (Wire frame stack)
17 HV planes
16 signal planes
  144 signal wires
All wires soldered to frames
Mounting hardware and fittings all constructed
PCB readout boards will arrive late March
Assembly March-April
Testing starting in April

## Slide 21
Target / Detector (Wire frame stack)

## Slide 22
Scope
  4 enclosures (one per vacuum feedthrough) with 36 channels each
  Circuit board designed locally at ORNL
  Connector to ion chamber vacuum port and cabling to DAQ module
Status
  Prototype circuit board tested
  Achieved theoretical limit on some channels, testing in progress
Remaining work
  Test cooled prototype
  inside enclosures
  Build final preamps
  Build cables
  Test all channels
  Measure instrumental
  asymmetries with spin
  rotator and target
Pre-amplifiers
Kabir Latiful
Irakli Garishvili
David Bowman

## Slide 23
Scope
  144 channels of 24 bit, 128 KS/s ADC
Progress
  Basic software used to take and analyze data
  Extensive testing of two prototype systems
  Preliminary measurements of instrumental false asymmetry
  ADCs ordered, delivery: April 9th; custom firmware by end of May
  Two DAQ computers acquired; RAID array ordered
Remaining work
  Test complete DAQ hardware: April–May
  Adjust software for final hardware and custom firmware: May–June
Data acquisition
Kabir Latiful
Irakli Garishvili
Nadia Fomin
Chris Crawford

## Slide 24
Measurements with RFSR, preamps, and ADC modules
Trigger optically isolated
Instrumental false asymmetry measurement
Kabir Latiful
Irakli Garishvili
David Bowman
Chris Crawford
Divider
Sig. Gen
Amp.
ADC
RFSR
optical isolator
dirty ground
clean ground
Fake T0
Preamp

## Slide 25
Data taken for 5 hours
A = (2.64 ± 1.64) x 10-10
Will repeat measurements with delivered DAQ and wire chamber
Instrumental false asymmetry measurement

## Slide 26
Schedule Overview
Complete component construction / bench testing now - May
Preassemble in staging are May - June
Facility summer maintenance break June-27 – Aug-15
Removal of NPDGamma June-27 – July -7
Installation of n-3He on beam line July-7 - Aug-15
IRR August
Alignment of the experiment with beam Sep – Oct -2014
Commissioning; 60 days Oct – Nov - 2014
Measurement of PC transverse asymmetry; 15 days Dec - 2014
Facility winter maintenance break Dec - 2014 - Feb - 2015
Measurement of PV longitudinal asymmetry; 200 days Feb-2015 – Dec- 2015

## Slide 27
Scope:
  Design of unistructure support frame
  Design, construction of mounting and alignment hardware
  Maintain 3d solid model of experiment
  Ensure components fit and that support frame matche the NPDGamma stands
Status:
  Preliminary solid model exists
  Conceptual design for mounts and alignment
  Model is added to beamline model by SNS designers
Remaining work:
  Final design of stand and mounting
  Construction of mounting, alignment hardware: April
  Assembly of complete system in staging area: May-June
  Alignment testing: June
Caleb Wickersham
Mark McCrea
Jack Thomison
Geoff Greene
Josh Hamblen
Integration / Pre-assembly

## Slide 28
Mounting / alignment components
  Aperture / crosshairs for beam scan
  Support stand and xy-adjustment for theodolite
  Alignment V-block for trimming B-field
  Optical system and adjustable mount for target
  10 mrad tolerance – no need for S/A crew
Alignment

## Slide 29
Scan beam profile upstream and transfer centroid to crosshairs
Scan beam profile downstream
Align theodolite to crosshairs
Align B-field to theodolite
Field map in RFSR/Target region
Align the position / angle of target with theodolite / autocollimator
Tune RSFR / measure polarization
Measure physics asymmetry
IRR #1
IRR #2
Commissioning / Run plan

## Slide 30
Backups

## Slide 31: n3He Calculations
Full four-body calculation of strong scattering wave functions
Evaluation of the weak matrix elements in terms of the DDH
  potential (Work in progress on calculation of EFT low energy
  coefficients)
M. Viviani, R. Schiavilla, Phys. Rev. C. 82 044001 (2010)
L. Girlanda et al. Phys. Rev. Lett. 105 232502 (2010)
DDH Weak Coupling | (ApZ) n3He tp
a1 | -0.189
a0 | -0.036
a1 | 0.019
a2 | -0.0006
a0 | -0.0334
a1 | 0.0413