## Budget
| n-3He Budget | [11 empty] | Version: 10/07/2009/ornl part 01/07/2013
[6 empty] | TOTAL |  | TOTAL | TOTALS | TOTALS | funding
| Item | Unit costs | Subtotal | Overhead |  | Burdened | Contingency |  | (operation) | (others) | in hand | Remarks | Responsible institute/leader
1 | Beam
1.1 | Beam monitors
1.1.1 | Fabricate holding structure |  | 300 | 26% | 78 | 378 | 30% | 113.4 |  | 491.4 |  |  | University shop
1.3 | Beam intensity monitor
1.3.1 | NPDGamma monitors |  | 0 | 0% | 0 | 0 | 0% | 0
1.3.2 | Build collimation for intensity studies |  | 0 | [9 empty] | University shop
1.3.3 | Build scanner support | [11 empty] | University shop
1.4 | Polarimetry
1.4.1 | Design polarimetry |  | 0 | 0% | 0 | 0 | 0% | 0
1.4.2 | Procure and construct polarimetry |  | 1000 | 26% | 260 | 1260 | 30% | 378 |  | 1638 |  |  | University shop
1.5 | Crafts for installation (2 for 1 day) |  | 880 | 40% | 352 | 1232 | 30% | 369.6 | 1601.6
| Beam Total |  | 2180 | 31.65% | 690 | 2870 | 30% | 861 | 1601.6 | 2129.4 | 0
2 | Magnetic Field
2.1 | Field Calculations |  | 0 | 26% | 0 |  | 30% | 0 |  |  |  |  | ASU / Ricardo
2.2 | Design coils |  | 3846.1538 | 26% | 1000 |  | 30% | 1453.8462 |  | 6300 | 6300 | CONACYT | UNAM / Libertad
2.3 | Procure and fabricate solenoid |  | 15384.6154 | 26% | 4000 |  | 30% | 5815.3846 |  | 25200 | 25200 | & UNAM
2.4 | Procure and fabricate transition field coil |  | 3000 | 26% | 780 |  | 30% | 1134 |  | 4914 |  |  | NCSU / Pil
2.5 | Design holders for shielding and coils |  | 5000 | 26% | 1300 |  | 30% | 1890 |  | 8190 |  |  | ORNL / Seppo
2.6 | Procure and fabricate holers |  | 10000 | 26% | 2600 |  | 30% | 3780 |  | 16380
2.7 | Field Monitoring |  | 2000 | 26% | 520 |  | 30% | 756 |  | 3276 |  |  | UVa / Stefan
2.71 | Design scanning mapper |  | 0
2.7.2 | Procure and fabricate mapper |  | 500 | 26% | 130 |  | 30% | 189 |  | 819
2.8 | Field Alignment |  | 0 | 40% | 0 |  | 30% | 0
| Magnetic Field Total |  | 39730.7692 | 26% | 10330 | 0 | 30% | 15018.2308 | 0 | 65079 | 31500
3 | RF Spin Flipper
3.1 | Design (coils, body, support) |  | 0 | 26% | 0 |  | 20% | 0 |  | 0 |  | NSF | UKy / Chris
3.2 | Procurement |  | 10000 | 26% | 2000 |  | 30% | 3600 |  | 15600 |  | NSF
3.3 | Electronics |  | 5000 | 26% | 1000 |  | 30% | 1800 |  | 7800 |  | NSF
3.4 | Installation crafts (2 for 1 day) |  | 880 | 40% | 352 | 1232 | 30% | 369.6 | 1601.6
| RF Spin Flipper Total |  | 15880 | 21.11% | 3352 | 1232 | 30% | 5769.6 | 1601.6 | 23400 | 0
4 | Target/detector
4.1 | Design of tgt/detector |  | 0 | 0% | 0 |  | 30% | 0 |  | 0 | 0 |  | Manitoba / Michael
4.2 | Procure wire chamber |  | 53846.1538
4.2.1 | Aluminum chamber | 19230.7692 |  | 0% | 0 |  | 30% | 5769.2308 |  | 25000 | 25000 | NSERC
4.2.2 | Macor wire frame | 10769.2308 |  | 0% | 0 |  | 30% | 3230.7692 |  | 14000 | 14000 | NSERC
4.2.3 | Copper wire (plated) - 1500 ft | 3076.9231 |  | 0% | 0 |  | 30% | 923.0769 |  | 4000 | 4000 | NSERC
4.2.4 | Helium 3 gas - 30 L | 11538.4615 |  | 0% | 0 |  | 30% | 3461.5385 |  | 15000 | 15000 | NSERC
4.2.5 | High voltage feedthroughs - 4 | 769.2308 |  | 0% | 0 |  | 30% | 230.7692 |  | 1000 | 1000 | NSERC
4.2.6 | Instrumentation feedthroughs - 10 | 7692.3077 |  | 0% | 0 |  | 30% | 2307.6923 |  | 10000 | 10000 | NSERC
4.2.7 | Gas feedthrough (1/2 in) - 2 | 769.2308 |  | 0% | 0 |  | 30% | 230.7692 |  | 1000 | 1000 | NSERC
4.3 | Gas handling system |  | 25384.6154
4.3.1 | Valves | 1538.4615 |  | 0% | 0 |  | 30% | 461.5385 |  | 2000 | 2000 | NSERC
4.3.2 | Pumping station | 19230.7692 |  | 0% | 0 |  | 30% | 5769.2308 |  | 25000 | 25000 | CFI
4.3.3 | Residual gas analyzer | 1538.4615 |  | 0% | 0 |  | 30% | 461.5385 |  | 2000 | 2000 | CFI
4.3.4 | Pressure gauges | 2307.6923 |  | 0% | 0 |  | 30% | 692.3077 |  | 3000 | 3000 | NSERC
4.3.5 | Heater and heating tape | 769.2308 |  | 0% | 0 |  | 30% | 230.7692 |  | 1000 | 1000 | NSERC
4.4 | Fabrication |  | 6153.8462
4.4.1 | Machining - 100 hrs | 3846.1538 |  | 0% | 0 |  | 30% | 1153.8462 |  | 5000 | 5000 | NSERC
4.4.2 | Nano Fabricationlab | 2307.6923 |  | 0% | 0 |  | 30% | 692.3077 |  | 3000 | 3000 | NSERC
4.5 | Chamber Assembly |  | 0
4.5.1 | Assembly of wire frame and wires | 0 |  | 0% | 0 |  | 30% | 0 |  | 0 | 0 | NSERC
4.5.2 | Installation and alignment of wire frame | 0 |  | 0% | 0 |  | 30% | 0 |  | 0 | 0 | NSERC
4.5.3 | Gas filling and testing | 0 |  | 0% | 0 |  | 30% | 0 |  | 0 | 0 | NSERC
4.6 | Procure chamber holder |  | 5000 | 20% | 1000 |  | 20% | 1200 |  | 7200
4.7 | Installation - crane (2 guys 1/2 day) |  | 440 | 40% | 176 | 616 | 30% | 184.8 | 800.8
4.8 | Detector alignment (alignment folks) |  | 0 | 40% | 0 | 0 | 20% | 0 | 0
| Target/Detector Total |  | 90824.6154 | 1.295% | 1176 | 616 | 29.35% | 27000.1846 | 800.8 | 118200 | 111000
5 | Electronics
5.1 | Electronics |  | 18923.0769
5.1.1 | 4x32ch preamp modules | 12000 |  | 40% | 4800 | 16800 | 30% | 5040 | 21840
5.1.2 | High voltage power supply - 1 | 2307.6923 |  | 0% | 0 |  | 30% | 692.3077 |  | 3000 | 3000
5.1.3 | Low voltage power supplies 2x from NPDGamma | 769.2308 |  | 0% | 0 |  | 30% | 230.7692 |  | 1000 | 1000
5.1.4 | Cables | 3846.1538 |  | 0% | 0 |  | 30% | 1153.8462 |  | 5000 | 5000
| Electronics Total |  | 18923.0769 |  | 4800 | 0 |  | 7116.9231 | 21840 | 9000 | 9000
5 | DAQ system
5.1 | Digitization |  | 27600 | [9 empty] | UKy / Chris
5.1.3 | Crate and 96ch digitizer cards | 21000 |  | 40% | 8400 | 29400 | 30% | 8820 | 38220
5.1.4 | Trigger Module | 3000 |  | 26% | 780 |  | 30% | 1134 |  | 4914
5.1.5 | Auxilliary electronics | 3000 |  | 40% | 1200 | 4200 | 30% | 1260 | 5460
5.1.6 | Cables from preamps (SCSI) | 600 |  | 40% | 240 | 840 | 30% | 252 | 1092
5.2 | Data transfer and storage |  | 15000
5.2.1 | Workstations from NPDGamma | 0 |  | 26% | 0 |  | 15% | 0 | 0
5.2.2 | Raid storage array | 15000 |  | 40% | 6000 | 21000 | 20% | 4200 | 25200
| DAQ System Total |  | 42600 | 39.01% | 16620 | 55440 | 26.45% | 15666 | 69972 | 4914 | 0
7 | Shielding/collimation
7.1 | Neutron shielding and supports |  | 5000 | 26% | 1300 |  | 30% | 1890 |  | 8190 |  |  | UNH / John
7.2 | Collimation and supports |  | 1500 | 26% | 390 |  | 30% | 567 |  | 2457
7.3 | Crafts (2 guys for 1 day) |  | 880 | 40% | 352 | 1232 | 30% | 369.6 | 1601.6
| Shielding/Collimation Total |  | 6500 | 26% | 1690 | 1232 | 30% | 2457 | 1601.6 | 10647 | 0
8 | Common stand for experiment
8.1 | Design of common stand | 0
8.2 | Engineering review of stand | 6000 | 6000 | 40% | 2400 | 8400 | 30% | 2520 | 10920
8.3 | Procure and construct stand | [11 empty] | CONACYT/UNAM
8.4 | Install beamline
8.4.1 | Craning (4 guys 1/2 day) stand in and closing the cace roof) | 880 | 880 | 40% | 352 | 1232 | 30% | 369.6 | 1601.6
8.4.2 | Install (craft 2 guys 1 day) | 880 | 880 | 40% | 352 | 1232 | 30% | 369.6 | 1601.6
| Common Stand Total |  | 7760 | 0% | 3104 | 10864 | 0% | 3259.2 | 14123.2
9 | Shop time/ Engineering &Reviews
9.1 | Engineering support (1 week=40h) |  | 6000 | 40% | 2400 | 8400 | 30% | 2520 | 10920
9.2 | Draft support (2weeks) integration to model |  | 4400 | 40% | 1760 | 6160 | 30% | 1848 | 8008
9.3 | Pdiv/SNS shop time (1 week) |  | 3000 | 40% | 1200 | 4200 | 30% | 1260 | 5460
9.4 | Verification of rad MCNP calcualtions (a week) |  | 6000 | 40% | 2400 | 8400 | 30% | 2520 | 10920
9.5 | SNS QA for 2 days |  | 2400 | 40% | 960 | 3360 | 30% | 1008 | 4368
9.6 | Miscellaneous materials |  | 3500 | 40% | 1400 | 4900 | 30% | 1470 | 6370
| Shop time/Engineering Total |  | 25300 | 40% | 10120 | 35420 | 30% | 10626 | 46046
10 | Removing NPDGamma apparatus
10.1 | Opening cave roof (4 guys 1/2 day) |  | 880 | 40% | 352 | 1232 | 30% | 369.6 | 1601.6
10.2 | Disconnectiong NPDGamma apparatus (2 crafts 2 days) |  | 1760 | 40% | 704 | 2464 | 30% | 739.2 | 3203.2
10.3 | Crane components out (craft 4 guys 1 day) |  | 1760 | 40% | 704 | 2464 | 30% | 739.2 | 3203.2
| Removal Total |  | 4400 | 40% | 1760 | 6160 |  | 1848 | 8008 | 0 | 0
| Total |  | 254098.4615 |  | 53642 | 113834 |  | 89622.1385 | 163993.2 | 233369.4 | 151500
| Overhead for DOE grant | 20%
| Overhead for ORNL labor | 40%
| Overhead for ORNL material | 40%
| Overhead ASU | 26%
| Overhead at Manitoba | 0%
| Overhead Kentacky | 26%
| Overhead UNAM | 0%
| Overhead UNH | 26%

## Schedule
| n-3He Schedule | [17 empty] | Funding Profile
|  | FY09 |  | FY10 |  |  |  | FY11 |  |  |  | FY12 |  |  |  | FY13 |  |  | FY09 |  | FY10 |  | FY11 |  | FY12
| Item | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 |  | DOE | Other | DOE | Other | DOE | Other | DOE | Other
1 | Polarized Beam
1.1 | Polarizer | [19 empty] | #NAME? | #NAME? | bar: FY10 3 to FY11 1
1.2 | Beam monitors (stands and shielding) | [19 empty] | 0 | 0 | bar: FY10 3 to FY11 1
1.3 | Beam polarization measurement | [21 empty] | 0 | 0 | bar: FY11 3; FY12 4
1.4 | Beam alignment | [21 empty] | 1601.6 | 0 | bar: FY11 3
| Polarized Beam Milestones | [16 empty] | Total: | 0 | 0 | #NAME? | #NAME? | 1601.6 | 0 | 0 | 0 | bar: FY11 3; FY12 4
2 | RF Spin Flipper
2.1 | Design (coils, body, support) | [17 empty] | #NAME? | #NAME? | bar: FY09 3 to FY09 4
2.2 | Procurement | [19 empty] | #NAME? | #NAME? | bar: FY10 1 to FY10 2
2.4 | Electronics | [19 empty] | #NAME? | #NAME? | bar: FY10 1 to FY10 2
2.3 | Installation in FNPB | [21 empty] | #NAME? | #NAME? | bar: FY11 3
| RF Spin Flipper Milestones | FY10 1: a; FY10 3: b; FY11 1: c | Total: | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0
3 | Magnetic Fields
3.1 | Field Calculations | [17 empty] | 0 | 0 | bar: FY09 3 to FY09 4
3.2 | Design coils | [17 empty] | 0 | 6300 | bar: FY09 4 to FY10 2
3.4 | Procure solenoid | [19 empty] | 0 | 25200 | bar: FY10 3 to FY11 1
3.3 | Procure transition field coil | [19 empty] | 0 | 4914 | bar: FY10 3 to FY11 1
3.5 | Design stands for shielding and coils | [19 empty] | 0 | 8190 | bar: FY10 3
3.6 | Procure stands | [21 empty] | 0 | 16380 | bar: FY10 4 to FY11 1
3.7 | Field Monitoring | [21 empty] | 0 | 3276 | bar: FY11 1 to FY12 4
3.8 | Installation at FNPB | [21 empty] | #NAME? | #NAME? | bar: FY11 3
3.8 | Field Alignment | [21 empty] | 0 | 0 | bar: FY11 3 to FY11 4
| Magnetic Fields and Shields Milestones | FY10 2: a; FY11 1: b; FY11 3: c; FY11 4: d | Total: | 0 | 6300 | 0 | 38304 | #NAME? | #NAME? | 0 | 0
4 | Target/detector
4.1 | Design of tgt/detector | [17 empty] | 0 | 0 | bar: FY09 3 to FY10 1
4.2 | Procure wire chamber | [19 empty] | 0 | 0 | bar: FY10 1 to FY10 3
4.2.1 | Aluminum chamber | [19 empty] | 0 | 25000 | bar: FY10 1
4.2.2 | Macor wire frame | [19 empty] | 0 | 14000 | bar: FY10 1 to FY10 2
4.2.3 | Copper wire (plated) - 1500 ft | [19 empty] | 0 | 4000 | bar: FY10 1 to FY10 2
4.2.4 | Helium 3 gas - 30 L | [19 empty] | 0 | 15000 | bar: FY10 1 to FY10 2
4.2.5 | High voltage feedthroughs - 4 | [19 empty] | 0 | 1000 | bar: FY10 1 to FY10 2
4.2.6 | Instrumentation feedthroughs - 10 | [19 empty] | 0 | 10000 | bar: FY10 1 to FY10 2
4.2.7 | Gas feedthrough (1/2 in) - 2 | [19 empty] | 0 | 1000 | bar: FY10 1 to FY10 2
4.3 | Electronics | [19 empty] | #NAME? | #NAME? | bar: FY10 1 to FY10 2
4.3.1 | Preamplifiers - 400 ch | [19 empty] | #NAME? | #NAME? | bar: FY10 1 to FY10 2
4.3.2 | High voltage power supply - 1 | [19 empty] | #NAME? | #NAME? | bar: FY10 2 to FY10 3
4.3.3 | Low voltage power supplies - 2 | [19 empty] | #NAME? | #NAME? | bar: FY10 2 to FY10 3
4.3.5 | Cables - 400 | [19 empty] | #NAME? | #NAME? | bar: FY10 2 to FY10 3
4.4 | Gas handling system | [19 empty] | 0 | 0 | bar: FY10 2 to FY10 3
4.4.1 | Valves | [19 empty] | 0 | 2000 | bar: FY10 2 to FY10 3
4.4.2 | Pumping station | [19 empty] | 0 | 25000 | bar: FY10 2 to FY10 3
4.4.3 | Residual gas analyzer | [19 empty] | 0 | 2000 | bar: FY10 2 to FY10 3
4.4.4 | Pressure gauges | [19 empty] | 0 | 3000 | bar: FY10 2 to FY10 3
4.4.5 | Heater and heating tape | [19 empty] | 0 | 1000 | bar: FY10 2 to FY10 3
4.5 | Fabrication | [19 empty] | 0 | 0 | bar: FY10 3
4.5.1 | Machining - 100 hrs | [19 empty] | 0 | 5000 | bar: FY10 3
4.5.2 | Nano Fabricationlab | [19 empty] | 0 | 3000 | bar: FY10 3
4.6 | Chamber Assembly | [19 empty] | 0 | 0 | bar: FY10 4 to FY11 2
4.6.1 | Assembly of wire frame and wires | [19 empty] | 0 | 0 | bar: FY10 4 to FY11 1
4.6.2 | Installation and alignment of wire frame | [19 empty] | 0 | 0 | bar: FY11 2
4.6.3 | Gas filling and testing | [19 empty] | 0 | 0 | bar: FY11 2
4.7 | Procure stand | [21 empty] | 0 | 7200 | bar: FY11 1 to FY11 2
4.8 | Installation at FNPB | [21 empty] | 800.8 | 0 | bar: FY11 3 to FY11 4
4.9 | Detector alignment | [21 empty] | 0 | 0 | bar: FY11 3 to FY11 4
| Target/Detector Milestones | FY10 1: a; FY10 2: bc; FY10 4: de; FY11 2: f; FY11 3: g; FY11 4: h | Total: | 0 | 0 | #NAME? | #NAME? | 800.8 | 7200 | 0 | 0
5 | DAQ system
5.1 | Digitization | [19 empty] | 0 | 0 | bar: FY10 1 to FY10 4
5.1.1 | VME Crate | [19 empty] | #NAME? | #NAME? | bar: FY10 1 to FY10 4
5.1.2 | Single Board Computers | [19 empty] | #NAME? | #NAME? | bar: FY10 1 to FY10 4
5.1.3 | Digitizers | [19 empty] | 38220 | 0 | bar: FY10 1 to FY10 4
5.1.4 | Trigger Module | [19 empty] | 0 | 4914 | bar: FY10 1 to FY10 4
5.1.5 | Auxilliary electronics | [19 empty] | 5460 | 0 | bar: FY10 1 to FY10 4
5.1.6 | Cables | [19 empty] | 1092 | 0 | bar: FY10 1 to FY10 4
5.2 | Data transfer and storage | [21 empty] | 0 | 0 | bar: FY11 2
5.2.1 | Workstation | [21 empty] | 0 | 0 | bar: FY11 2
5.2.2 | Raid storage array | [21 empty] | 25200 | 0 | bar: FY11 2
| DAQ System Milestones | [16 empty] | Total: | 0 | 0 | #NAME? | #NAME? | 25200 | 0 | 0 | 0 | bar: FY10 3; FY11 1
6 | Shielding/collimation
6.1 | Neutron shielding | [21 empty] | 0 | 8190 | bar: FY10 4 to FY11 4
6.2 | Collimation | [21 empty] | 0 | 2457 | bar: FY10 4 to FY11 4
| Shielding/Collimation Milestones | [16 empty] | Total: | 0 | 0 | 0 | 0 | 0 | 10647 | 0 | 0 | bar: FY11 4
7 | Alignment
7.1 | Survey technician - 2 wks | [21 empty] | #NAME? | #NAME? | bar: FY11 4
| Alignment Milestones | [16 empty] | Total: | 0 | 0 | 0 | 0 | #NAME? | #NAME? | 0 | 0 | bar: FY11 3 to FY11 4
8 | Operating costs
8.1 | Operation | [21 empty] | #NAME? | #NAME? | bar: FY11 3 to FY12 4
| Operating costs Milestones | FY11 4: a; FY12 1: bc; FY12 4: d; FY13 2: ...e | Total: | 0 | 0 | 0 | 0 | #NAME? | #NAME? | 0 | 0
[18 empty] | Grand Total: | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0 | 0